## Gant
Task	Work (h)	Duration (days)	13	13	13	13	13	13	13	14	14	14	14	14	14	14	15	15	15	15	15	15	15	16	16	16	16	16	16	16	17	17	17	17	17	17	17	18	18	18	18	18	18	18	19	19	19	19	19	19	19	20	20	20	20	20	20	20	21	21	21	21	21
Pacman	415	60	må 26-mar 12	ti 27-mar 12	on 28-mar 12	to 29-mar 12	fr 30-mar 12	lö 31-mar 12	sö 01-apr 12	må 02-apr 12	ti 03-apr 12	on 04-apr 12	to 05-apr 12	fr 06-apr 12	lö 07-apr 12	sö 08-apr 12	må 09-apr 12	ti 10-apr 12	on 11-apr 12	to 12-apr 12	fr 13-apr 12	lö 14-apr 12	sö 15-apr 12	må 16-apr 12	ti 17-apr 12	on 18-apr 12	to 19-apr 12	fr 20-apr 12	lö 21-apr 12	sö 22-apr 12	må 23-apr 12	ti 24-apr 12	on 25-apr 12	to 26-apr 12	fr 27-apr 12	lö 28-apr 12	sö 29-apr 12	må 30-apr 12	ti 01-maj 12	on 02-maj 12	to 03-maj 12	fr 04-maj 12	lö 05-maj 12	sö 06-maj 12	må 07-maj 12	ti 08-maj 12	on 09-maj 12	to 10-maj 12	fr 11-maj 12	lö 12-maj 12	sö 13-maj 12	må 14-maj 12	ti 15-maj 12	on 16-maj 12	to 17-maj 12	fr 18-maj 12	lö 19-maj 12	sö 20-maj 12	må 21-maj 12	ti 22-maj 12	on 23-maj 12	to 24-maj 12	fr 25-maj 12
Meetings	32	16	2				2			2							2				2			2				2			2				2			2				2			2				2			2				2			2
R-Reports	24	8						3							3							3							3							3							3							3							3
L-Reports	50	12					10																					15																					10										15
GitHub	5	1																		5
#ScreenManager	20	9																									20
BaseScreen	5	1																									5
GameScreen	5	1																																5
MenuScreen	5	2																																5
#CFGManager	2	1																										2
Entries	2	1																										2
Links	2	1																										2
Containers	2	1																										2
Load/Map	2	1																										2
#D3DManager	20	8																										20
Layout2D	2	2																										2
Shader2D	10	2																										10
Layout3D	2	2																															2
Shader3D	10	2																															10
#InputManager	5	1																										5
Events	15	7																										15
#Camera	2	2																															2
Events	8	1																																8
#GUI	4	4																															4
Entries	2	1																															2
ButtonComponents	5	2																															5
GE-2D (background)	1	2																																							1
Events	8	2																																8
#Modeling	0	…
Spirits	5	1																																						5
Pills	5	1																																						5
#GameEntity (GE)	10	14																																						10
2D	5	1																																						5
Sprites	5	1																																						5
3D	5	9																																							5
GEComponents (base)	5	9																																							5
SFX	5	2																																																						5
Render	10	9																																							10
AI	5	3																																														5
Movables	5	2																																															5
Statics	10	2																																						10
#GE_Handler	5	12																																								5
Events	5	7																																								5
#AI	10	14																																														10
Graph	5	1																																														5
Pathfindig (Dijkstras	5	1																																														5
Events	10	2																																															10
Personality	5	4																																																								5
#Loader	5	3																																														5
RawImageReader	5	1																																														5
Distributable	10	3																																														10
#SoundManager	10	4																																																				10
Entries	5	2																																																				5
Events	10	1																																																						10
Total Workload:	415	Weekly Total:	17						Weekly Total:	5						Weekly Total:	12						Weekly Total:	109						Weekly Total:	58						Weekly Total:	78						Weekly Total:	77						Weekly Total:	42						Weekly Total:	17

## Schedule
Area	Objectives	Requirement	StartDate	EndDate	Objective/days	Area/days	TimeEstimate (h)	Total Time (h)	Invested Time (h)	TotInv Time (h)	Completion	Area completion	Investment/payoff ratio	Participants		Area	StartDate	EndDate	Week	Days	TimeEstimate (h)	InvestedTime (h)	Completion	Inv/Pay Ratio	Participants	Notes
ScreenManager	#ScreenManager		12-04-19	12-04-27	9	13	20	35	2	2	10%	15,00%	0,01:1	chpe10		GitHub	12-04-12	12-04-15	15	3	5	5	100%	1,00:1	chjo10, jolo10
	BaseScreen		12-04-19	12-04-19	1		5		2		50%			chpe10		R1	12-03-26	12-04-02	14	7	3	?	100%	#VALUE!	vist10	substandard
	GameScreen	BaseScreen	12-04-26	12-04-26	1		5		0		0%					R2	12-04-02	12-04-09	15	7	3	3	100%	1,00:1	chpe10	substandard
	MenuScreen	BaseScreen	12-04-26	12-04-27	2		5	35	0		0%					R3	12-04-09	12-04-16	16	7	3	3	100%	1,00:1	chpe10	substandard
CFGManager	#CFGManager		12-04-20	12-04-20	1	5	2	10	2	7	90%	98,00%	0,69:1	chpe10		R4	12-04-16	12-04-23	17	7	3			0,00:1
	Entries		12-04-20	12-04-20	1		2		1		100%			chpe10		R5	12-04-23	12-04-30	18	7	3			0,00:1
	Links	Entries	12-04-20	12-04-20	1		2		1		100%			chpe10		R6	12-04-30	12-05-07	19	7	3			0,00:1
	Containers	Links	12-04-20	12-04-20	1		2		1		100%			chpe10		R7	12-05-07	12-05-14	20	7	3			0,00:1
	Load/Map	Containers	12-04-20	12-04-20	1		2		2		100%			chpe10		L1	12-03-26	12-04-05	14	10	10	?	100%	#VALUE!	chpe10, chjo10, vist10	rejected
D3DManager	#D3DManager		12-04-20	12-04-27	8	16	20	44	2	2	10%	2,00%	0,00:1	chpe10		L2	12-04-05	12-04-27	17	22	15			0,00:1
	Layout2D		12-04-20	12-04-21	2		2		0		0%					L3	12-04-27	12-05-14	20	17	10			0,00:1
	Shader2D	Layout2D	12-04-20	12-04-21	2		10		0		0%					L4	12-05-14	12-05-25	21	11	15			0,00:1
	Layout3D		12-04-25	12-04-26	2		2		0		0%									Total Time:	76	11
	Shader3D	Layout3D	12-04-25	12-04-26	2		10		0		0%
InputManager	#InputManager		12-04-20	12-04-20	1	8	5	20	4	4	75%	37,50%	0,80:1	jolo10, chjo10	Entire Time Distribution / by relative size and estimated hours
	Events		12-04-20	12-04-26	7		15		0		0%
Camera	#Camera		12-04-25	12-04-26	2	3	2	10	2	2	90%	45,00%	0,09:1	hehe10, vist10
	Events	D3DManager & InputManager	12-04-26	12-04-26	1		8		0		0%
GUI	#GUI		12-04-25	12-04-28	4	11	4	20	0	0	0%	0,00%	0,00:1
	Entries		12-04-25	12-04-25	1		2		0		0%
	ButtonComponents	InputManager	12-04-25	12-04-26	2		5		0		0%
	GE-2D (background)	Shader 2D & GameEntity2D	12-05-02	12-05-03	2		1		0		0%
	Events	ButtonComponents	12-04-26	12-04-27	2		8		0		0%
Modeling	#Modeling		12-05-02	12-05-02	0	2	0	10	0	0	0%	0,00%	0,00:1
	Spirits		12-05-02	12-05-02	1		5		0		0%
	Pills		12-05-02	12-05-02	1		5		0		0%
GameEntity (GE)	#GameEntity (GE)		12-05-02	12-05-25	24	62	10	65	0	0	0%	0,00%	0,00:1
	2D		12-05-02	12-05-02	1		5		0		0%
	Sprites	2D	12-05-02	12-05-02	1		5		0		0%
	3D		12-05-03	12-05-11	9		5		0		0%
	GEComponents (base)	3D & 2D	12-05-03	12-05-11	9		5		0		0%
	SFX	GEC(Base) & SoundManager	12-05-18	12-05-19	2		5		0		0%
	Render	GEC (base)	12-05-04	12-05-12	9		10		0		0%
	AI	3D	12-05-10	12-05-12	3		5		0		0%
	Movables	3D, Camera, Statics & (AI)	12-05-11	12-05-12	2		5		0		0%
	Statics	3D & CFGManager	12-05-02	12-05-03	2		10		0		0%
GE_Handler	#GE_Handler		12-05-04	12-05-20	17	24	5	10	0	0	0%	0,00%	0,00:1
	Events	GE	12-05-04	12-05-10	7		5		0		0%
AI	#AI		12-05-10	12-05-25	16	23	10	40	0	0	0%	0,00%	0,00:1
	Graph		12-05-10	12-05-10	1		5		0		0%
	Pathfindig (Dijkstras	Graph	12-05-10	12-05-10	1		5		0		0%
	Events	GE_Handler	12-05-11	12-05-12	2		10		0		0%
	Personality	Events	12-05-23	12-05-25	3		10		0		0%
Loader	#Loader		12-05-10	12-05-12	3	7	5	20	0	0	0%	0,00%	0,00:1
	RawImageReader	CFGManager	12-05-10	12-05-10	1		5		0		0%
	Distributable	RIR, GE_H & Modeling	12-05-10	12-05-12	3		10		0		0%
SoundManager	#SoundManager		12-05-16	12-05-19	4	7	10	25	0	0	0%	0,00%	0,00:1
	Entries		12-05-16	12-05-17	2		5		0		0%
	Events	Entries	12-05-18	12-05-18	1		10		0		0%
						Total Time:	309		AC:	19	SPI:	16,46%	note: good% < 1 < bad%

## Time Reports
Week13	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)		Week14	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)
Meetings	4					4		Meetings	2					2
Code	0					0		Code	0					0
Studies	2					2		Studies	3					3
Reports	0					0		Reports	4					4
Misc	0					0		Misc	0					0
Total	6	0	0	0	0	6		Total	9	0	0	0	0	9

Week15	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)		Week16	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)
Meetings	4					4		Meetings	2					2
Code	0					0		Code	11					11
Studies	2					2		Studies	0					0
Reports	3					3		Reports	0					0
Misc	5					5		Misc	1					1
Total	14	0	0	0	0	14		Total	14	0	0	0	0	14

Week17	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)		Week18	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)
Meetings	0					0		Meetings	0					0
Code	0					0		Code	0					0
Studies	0					0		Studies	0					0
Reports	0					0		Reports	0					0
Misc	0					0		Misc	0					0
Total	0	0	0	0	0	0		Total	0	0	0	0	0	0

Week19	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)		Week20	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)
Meetings	0					0		Meetings	0					0
Code	0					0		Code	0					0
Studies	0					0		Studies	0					0
Reports	0					0		Reports	0					0
Misc	0					0		Misc	0					0
Total	0	0	0	0	0	0		Total	0	0	0	0	0	0

Week21	chpe10	hehe10	jolo10	chjo10	vist10	Invested Time (h)
Meetings	0					0
Code	0					0
Studies	0					0
Reports	0					0
Misc	0					0
Total	0	0	0	0	0	0

Week	PV (h)	AC (h)	EV (h)	EV (%)		Week	PV (h) stack	AC (h) stack	EV (h) stack	EV (%)
13	40	6		0,00%		13	40	6	0	0,00%
14	50	9	3	33,33%		14	90	15	3	20,00%
15	50	14	8	57,14%		15	140	29	11	37,93%
16	60	14	8	57,14%		16	200	43	19	44,19%
17	100			#DIV/0!		17	300	43	19	44,19%
18	60			#DIV/0!		18	360	43	19	44,19%
19	80			#DIV/0!		19	440	43	19	44,19%
20	45			#DIV/0!		20	485	43	19	44,19%
21	20			#DIV/0!		21	505	43	19	44,19%
Total:	505	43	19	#DIV/0!
Divided EV Track / Time (week) / Effort (hours)										Stacked EV Track / Time (total weeks) / Effort (total hours)