## Gant
Task	Work (h)	Duration (days)	13					14					15					16					17					18					19					20					21
Pacman	415	60	må 26-mar 12	ti 27-mar 12	on 28-mar 12	to 29-mar 12	fr 30-mar 12	lö 31-mar 12	sö 01-apr 12	må 02-apr 12	ti 03-apr 12	on 04-apr 12	to 05-apr 12	fr 06-apr 12	lö 07-apr 12	sö 08-apr 12	må 09-apr 12	ti 10-apr 12	on 11-apr 12	to 12-apr 12	fr 13-apr 12	lö 14-apr 12	sö 15-apr 12	må 16-apr 12	ti 17-apr 12	on 18-apr 12	to 19-apr 12	fr 20-apr 12	lö 21-apr 12	sö 22-apr 12	må 23-apr 12	ti 24-apr 12	on 25-apr 12	to 26-apr 12	fr 27-apr 12	lö 28-apr 12	sö 29-apr 12	må 30-apr 12	ti 01-maj 12	on 02-maj 12	to 03-maj 12	fr 04-maj 12	lö 05-maj 12	sö 06-maj 12	må 07-maj 12	ti 08-maj 12	on 09-maj 12	to 10-maj 12	fr 11-maj 12	lö 12-maj 12	sö 13-maj 12	må 14-maj 12	ti 15-maj 12	on 16-maj 12	to 17-maj 12	fr 18-maj 12	lö 19-maj 12	sö 20-maj 12	må 21-maj 12	ti 22-maj 12	on 23-maj 12	to 24-maj 12	fr 25-maj 12
Meetings	32	16	2				2			2					2				2			2				2			2				2			2				2			2				2			2				2			2
R-Reports	24	8					3					3					3					3					3					3					3					3
L-Reports	50	12					10					15					10					15
GitHub	5	1					5
#ScreenManager	20	9					20
BaseScreen	5	1					5
GameScreen	5	1					5
MenuScreen	5	2					5
#CFGManager	2	1					2
Entries	2	1					2
Links	2	1					2
Containers	2	1					2
Load/Map	2	1					2
#D3DManager	20	8					20
Layout2D	2	2					2
Shader2D	10	2					10
Layout3D	2	2					2
Shader3D	10	2					10
#InputManager	5	1					5
Events	15	7					15
#Camera	2	2					2
Events	8	1					8
#GUI	4	4					4
Entries	2	1					2
ButtonComponents	5	2					5
GE-2D (background)	1	2					1
Events	8	2					8
#Modeling	0	…
Spirits	5	1					5
Pills	5	1					5
#GameEntity (GE)	10	14					10
2D	5	1					5
Sprites	5	1					5
3D	5	9					5
GEComponents (base)	5	9					5
SFX	5	2					5
Render	10	9					10
AI	5	3					5
Movables	5	2					5
Statics	10	2					10
#GE_Handler	5	12					5
Events	5	7					5
#AI	10	14					10
Graph	5	1					5
Pathfindig (Dijkstras	5	1					5
Events	10	2					10
Personality	5	4					5
#Loader	5	3					5
RawImageReader	5	1					5
Distributable	10	3					10
#SoundManager	10	4					10
Entries	5	2					5
Events	10	1					10
Total Workload:	415	Weekly Total:	17					Weekly Total:	5					Weekly Total:	12					Weekly Total:	109					Weekly Total:	58					Weekly Total:	78					Weekly Total:	77					Weekly Total:	42					Weekly Total:	17

## Schedule
Area	Objectives	Requirement	StartDate	EndDate	Objective/days	Area/days	TimeEstimate (h)	Total Time (h)	Invested Time (h)	TotInv Time (h)	Completion	Area completion	Investment/payoff ratio	Participants		Area	StartDate	EndDate	Week	Days	TimeEstimate (h)	InvestedTime (h)	Completion	Inv/Pay Ratio	Participants	Notes
ScreenManager	#ScreenManager		12-04-19	12-04-27	9	13	20	35	2	2	10%	15,00%	0,01:1	chpe10		GitHub	12-04-12	12-04-15	15	3	5	5	100%	1,00:1	chjo09, jolo09
	BaseScreen		12-04-19	12-04-19	1		5		2		50%			chpe10		R1	12-03-26	12-04-02	14	7	3	?	100%	#VALUE!	vist09	substandard
	GameScreen	BaseScreen	12-04-26	12-04-26	1		5		0		0%					R2	12-04-02	12-04-09	15	7	3	3	100%	1,00:1	chpe10	substandard
	MenuScreen	BaseScreen	12-04-26	12-04-27	2		5		0		0%					R3	12-04-09	12-04-16	16	7	3	3	100%	1,00:1	chpe10	substandard
CFGManager	#CFGManager		12-04-20	12-04-20	1	5	2	10	2	7	100%	98,00%	0,69:1	chpe10		R4	12-04-16	12-04-23	17	7	3			0,00:1
	Entries		12-04-20	12-04-20	1		2		1		100%			chpe10		R5	12-04-23	12-04-30	18	7	3			0,00:1
	Links	Entries	12-04-20	12-04-20	1		2		1		100%			chpe10		R6	12-04-30	12-05-07	19	7	3			0,00:1
	Containers	Links	12-04-20	12-04-20	1		2		1		100%			chpe10		R7	12-05-07	12-05-14	20	7	3			0,00:1
	Load/Map	Containers	12-04-20	12-04-20	1		2		2		100%			chpe10		L1	12-03-26	12-04-05	14	10	10	?	100%	#VALUE!	chpe10, chjo09, vist09	rejected
D3DManager	#D3DManager		12-04-20	12-04-27	8	16	20	44	2	2	10%	2,00%	0,00:1	chpe10		L2	12-04-05	12-04-27	17	22	15			0,00:1
	Layout2D		12-04-20	12-04-21	2		2		0		0%					L3	12-04-27	12-05-14	20	17	10			0,00:1
	Shader2D	Layout2D	12-04-20	12-04-21	2		10		0		0%					L4	12-05-14	12-05-25	21	11	15			0,00:1
	Layout3D		12-04-25	12-04-26	2		2		0		0%									Total Time:	76	11
	Shader3D	Layout3D	12-04-25	12-04-26	2		10		0		0%
InputManager	#InputManager		12-04-20	12-04-20	1	8	5	20	4	4	100%	37,50%	0,80:1	jolo09, chjo09		Entire Time Distribution
	Events		12-04-20	12-04-26	7		15		0		0%
Camera	#Camera		12-04-25	12-04-26	2	3	2	10	2	2	100%	45,00%	0,09:1	hehe10, vist09
	Events	D3DManager & InputManager	12-04-26	12-04-26	1		8		0		0%
GUI	#GUI		12-04-25	12-04-28	4	11	4	20	0	0	0%	0,00%	0,00:1
	Entries		12-04-25	12-04-25	1		2		0		0%
	ButtonComponents	InputManager	12-04-25	12-04-26	2		5		0		0%
	GE-2D (background)	Shader 2D & GameEntity2D	12-05-02	12-05-03	2		1		0		0%
	Events	ButtonComponents	12-04-26	12-04-27	2		8		0		0%
Modeling	#Modeling		12-05-02	12-05-02	0	2	0	10	0	0	0%	0,00%	0,00:1
	Spirits		12-05-02	12-05-02	1		5		0		0%
	Pills		12-05-02	12-05-02	1		5		0		0%
GameEntity (GE)	#GameEntity (GE)		12-05-02	12-05-25	24	62	10	65	0	0	0%	0,00%	0,00:1
	2D		12-05-02	12-05-02	1		5		0		0%
	Sprites	2D	12-05-02	12-05-02	1		5		0		0%
	3D		12-05-03	12-05-11	9		5		0		0%
	GEComponents (base)	3D & 2D	12-05-03	12-05-11	9		5		0		0%
	SFX	GEC(Base) & SoundManager	12-05-18	12-05-19	2		5		0		0%
	Render	GEC (base)	12-05-04	12-05-12	9		10		0		0%
	AI	3D	12-05-10	12-05-12	3		5		0		0%
	Movables	3D, Camera, Statics & (AI)	12-05-11	12-05-12	2		5		0		0%
	Statics	3D & CFGManager	12-05-02	12-05-03	2		10		0		0%
GE_Handler	#GE_Handler		12-05-04	12-05-20	17	24	5	10	0	0	0%	0,00%	0,00:1
	Events	GE	12-05-04	12-05-10	7		5		0		0%
AI	#AI		12-05-10	12-05-25	16	23	10	40	0	0	0%	0,00%	0,00:1
	Graph		12-05-10	12-05-10	1		5		0		0%
	Pathfindig (Dijkstras	Graph	12-05-10	12-05-10	1		5		0		0%
	Events	GE_Handler	12-05-11	12-05-12	2		10		0		0%
	Personality	Events	12-05-23	12-05-25	3		10		0		0%
Loader	#Loader		12-05-10	12-05-12	3	7	5	20	0	0	0%	0,00%	0,00:1
	RawImageReader	CFGManager	12-05-10	12-05-10	1		5		0		0%
	Distributable	RIR, GE_H & Modeling	12-05-10	12-05-12	3		10		0		0%
SoundManager	#SoundManager		12-05-16	12-05-19	4	7	10	25	0	0	0%	0,00%	0,00:1
	Entries		12-05-16	12-05-17	2		5		0		0%
	Events	Entries	12-05-18	12-05-18	1		10		0		0%
						Total Time:	309		AC:	19	SPI:	16,46%	note: good% < 1 < bad%

## Time_Reports
Week13	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)		Week14	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)
Meetings	4	4	4	4	4	4		Meetings	2	2	2	2	2	2
Code	0	0	0	0	0	0		Code	0	0	0	0	0	0
Studies	2	0	0	0	0	2		Studies	3	0	0	0	0	3
Reports	0	0	0	0	2	0		Reports	4	0	0	2	3	4
Misc	0	0	0	0	0	0		Misc	0	0	0	0	0	0
Total	6	0	0	0	0	6		Total	9	0	0	0	0	9

Week15	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)		Week16	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)
Meetings	4	4	4	4	4	4		Meetings	4	4	4	2	2	2
Code	0	0	0	0	0	0		Code	11	2	4	0	0	11
Studies	2	0	0	0	0	2		Studies	0					0
Reports	3	0	0	0	0	3		Reports	0					0
Misc	5	5	0	5	0	5		Misc	1					1
Total	14	0	0	0	0	14		Total	14	0	0	0	0	14

Week17	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)		Week18	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)
Meetings	0					0		Meetings	0					0
Code	0					0		Code	0					0
Studies	0					0		Studies	0					0
Reports	0					0		Reports	0					0
Misc	0					0		Misc	0					0
Total	0	0	0	0	0	0		Total	0	0	0	0	0	0

Week19	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)		Week20	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)
Meetings	0					0		Meetings	0					0
Code	0					0		Code	0					0
Studies	0					0		Studies	0					0
Reports	0					0		Reports	0					0
Misc	0					0		Misc	0					0
Total	0	0	0	0	0	0		Total	0	0	0	0	0	0

Week21	chpe10	hehe10	jolo09	chjo09	vist09	Invested Time (h)
Meetings	0					0
Code	0					0
Studies	0					0
Reports	0					0
Misc	0					0
Total	0	0	0	0	0	0

Week	PV (h)	AC (h)	EV (h)	EV (%)		Week	PV (h) stack	AC (h) stack	EV (h) stack	EV (%)
13	40	6		0,00%		13	40	6	0	0,00%
14	50	9	3	33,33%		14	90	15	3	20,00%
15	50	14	8	57,14%		15	140	29	11	37,93%
16	60	14	8	57,14%		16	200	43	19	44,19%
17	100			#DIV/0!		17	300	43	19	44,19%
18	60			#DIV/0!		18	360	43	19	44,19%
19	80			#DIV/0!		19	440	43	19	44,19%
20	45			#DIV/0!		20	485	43	19	44,19%
21	20			#DIV/0!		21	505	43	19	44,19%
Total:	505	43	19	#DIV/0!
Divided EV Track / Effort (hours) / Time (week)											Stacked EV Track / Effort (total hours) / Time (total weeks)